KUN / SUKI HRMS

Effort Estimate and Delivery Plan

| Field | Detail |
| --- | --- |
| Date | 25 August 2026 |
| Prepared for | KUN HRMS project — internal planning and client discussion |
| Scope basis | BRD sidebar: 14 modules, 203 screens |
| Supporting analysis | Legacy ERP schema (ERPDB_KUN_HRMS, 867 tables) and current codebase state |
| Status of estimate | Indicative, not committed — see Section 11 |

# Contents

# 1. Purpose

This document sets out the effort required to build the KUN HRMS in full. It identifies every management area the system must deliver, estimates each in developer-days, states the confidence behind each figure, and lists the assumptions and risks that would move the numbers.

The intent is transparency. Where a number is uncertain, that is stated rather than hidden inside an average.

# 2. How to read this estimate

## 2.1 Unit of measure

One developer-day means one developer working one full day on this project. Effort is not the same as calendar duration; Section 8 converts one to the other.

## 2.2 What a day estimate includes

Database model, API, user interface, validation, role-based access control, and developer self-testing.

## 2.3 What it excludes

Quality assurance, user acceptance testing, bug fixing, project management, requirement clarification meetings, deployment, training and documentation. These are estimated separately in Section 6.

## 2.4 Confidence levels

| Level | Meaning |
| --- | --- |
| High | The pattern is already built in this codebase, or fully specified by the legacy ERP. The estimate should hold within 20 per cent. |
| Medium | Structure is known, business rules are partly unknown. The estimate could move by 30 to 50 per cent. |
| Low | Business rules are unknown. The figure is a placeholder until the client answers. It could double. |

# 3. Current position

Twenty-one of 203 screens exist today: twenty master maintenance screens and the employee profile. The following are already built and materially reduce the cost of everything that follows: shared data table, form modal, confirmation dialog and field components; the application shell; the three-level navigation covering all 203 screens; and authentication.

Thirty-four Prisma models exist, covering organization masters, payroll and statutory definitions, role-based access control, and the employee record with its eleven related tables.

# 4. The 32 management areas

## 4.1 Foundation

| Management area | Screens | Days | Confidence | Basis for the estimate |
| --- | --- | --- | --- | --- |
| 1. Organization Management | 10 | 8 – 10 | High | Six of ten masters already exist. New: Company, Branch/Unit, Level rank, reporting structure, org chart. |
| 2. User & Access Management | 4 | 10 – 12 | Medium | Role and permission models exist; page-level permissions do not. 203 navigation nodes must be mapped and enforced. |
| 3. Approval Management | 15 | 12 – 15 | High | Legacy ERP supplies the design. Build the engine once, then 15 views reuse one component. Blocks eight other modules. |
| 4. Audit & Security Management | 3 | 8 – 10 | Medium | Audit log and write interceptor, session and password policy, salary field masking. |
| Foundation subtotal | 32 | 38 – 47 |  |  |

## 4.2 Employee lifecycle

| Management area | Screens | Days | Confidence | Basis for the estimate |
| --- | --- | --- | --- | --- |
| 5. Employee Management | 13 | 12 – 15 | High | Employee CRUD and 11 related models exist. Remaining work is profile tab screens. Repetitive and well understood. |
| 6. Recruitment Management | 12+ | 18 – 22 | Low | BRD shows offer letter onward; ERP runs a full candidate to induction pipeline. Drops to 8–10 days if offer-stage only. |
| 7. Joining / Onboarding | 8 | 8 – 10 | Medium | Checklist plus six statutory forms. Builds the PDF template engine reused by items 9 and 28. |
| 8. Lifecycle Management | 5 | 8 – 10 | High | Confirmation, transfer, promotion, designation change, increment. JobInfo versioning already exists. |
| 9. Letters & Certificates | 5 | 6 – 8 | High | Template plus merge fields plus PDF. Cheap once the template engine exists. |
| 10. Separation Management | 6 | 8 – 10 | Medium | Resignation, exit form, exit interview, no due, relieving. Must hand off to Full & Final settlement. |
| Employee lifecycle subtotal | 49 | 60 – 75 |  |  |

## 4.3 Time and attendance

| Management area | Screens | Days | Confidence | Basis for the estimate |
| --- | --- | --- | --- | --- |
| 11. Shift & Holiday Management | 6 | 10 – 12 | Medium | Holiday master, weekly off configuration, and a per-employee per-day roster grid. The grid is the expensive part. |
| 12. Attendance Management | 8 | 25 – 30 | Low | Hardest non-payroll area. eSSL integration, punch pairing, night shifts, grace minutes, LOM, mis-punch, mobile with geolocation, period lock. |
| 13. Leave Management | 7 | 15 – 18 | Low | Seven leave types, each with its own accrual, carry-forward bucket and encashment rule. The accrual engine is the risk. |
| 14. Overtime Management | 3 | 8 – 10 | Medium | ERP gives the shape: percentage by salary band and day type. Base and divisor still unknown. |
| 15. Comp-Off & Permission | 4 | 6 – 8 | Medium | Comp-off links a worked date to a comp-off date, consumed in minutes. Permission allowance rule not yet stated. |
| Time & attendance subtotal | 28 | 64 – 78 |  |  |

## 4.4 Compensation

| Management area | Screens | Days | Confidence | Basis for the estimate |
| --- | --- | --- | --- | --- |
| 16. Salary Structure Management | 6 | 15 – 18 | Medium | Component master, salary logic, effective-dated structure, CTC build-up, revision triggering arrears. |
| 17. Payroll Processing Engine | 9 | 30 – 40 | Low | Largest single item. Pro-rating, LOP and LOM, OT by day type, deductions, statutory, rounding, locking and reversal. Unreliable until formulas arrive. |
| 18. Statutory Management | 5 | 15 – 20 | Low | PF with per-employee configuration, ESI thresholds, PT, TDS, Tamil Nadu LWF, plus return formats. |
| 19. Deduction Management | 7 | 8 – 10 | High | Mostly simple per-month entry screens. Canteen is fed automatically from eSSL token logs. |
| 20. Loan Management | 4 | 8 – 10 | High | ERP defines the full cycle: master, apply, approve, issue with instalments, EMI recovery. |
| 21. Income Tax Management | 4 | 12 – 15 | Medium | Declaration across 27 categories, proof submission, annual projection, monthly TDS, old and new regime. |
| 22. Contract Labour Payroll | 4 | 10 – 12 | Low | A second payroll engine on a per-day basis with contractor service charge. Not in the BRD; scope must be confirmed. |
| 23. Benefits & Incentives | 4 | 10 – 12 | Low | Double-machine incentive reads machine allocation and production data from the manufacturing ERP. Integration risk. |
| 24. Payroll Output Management | 5 | 10 – 12 | Medium | Payslip individual and bulk, summary, bank transfer file, reconciliation. Bank format not yet supplied. |
| Compensation subtotal | 48 | 118 – 149 |  |  |

## 4.5 Supporting modules

| Management area | Screens | Days | Confidence | Basis for the estimate |
| --- | --- | --- | --- | --- |
| 25. Document Management | 6 | 10 – 12 | Medium | Indexes documents produced by other modules, with search, preview, download and access control. Depends on those modules existing. |
| 26. Learning & Development | 5 | 10 – 12 | Medium | Competency, skill matrix, skill levels, training plan and calendar. ERP also tracks scores and feedback. |
| 27. Visitor & Gate Management | 3 | 8 – 10 | Medium | Gate inward and outward, visitor pass with approval, photo capture. Self-contained, low dependency. |
| 28. Compliance Management | 6 | 12 – 15 | Medium | Tamil Nadu Factories Rules Forms 25, 15, 25B, 25C, 21, 22. Layouts fixed; depends on attendance, leave and payroll being correct. |
| 29. Employee Self Service | 10 | 12 – 15 | Medium | Ten screens that must work well on mobile, which is where most of the effort goes. |
| 30. Reports Management | 36 | 30 – 35 | Medium | Shared report framework first (about 5 days), then roughly 0.75 days per report. Some finance reports have no data source yet. |
| 31. Dashboard Management | 10 | 8 – 10 | High | Ten KPI views over data other modules already produce. Chart and card components exist. |
| 32. Notification Management | 3 | 8 – 10 | Medium | Email and WhatsApp configuration plus event triggers. Cost scales with the event list, not yet supplied. |
| Supporting subtotal | 79 | 88 – 109 |  |  |

## 4.6 Cross-cutting

| Management area | Screens | Days | Confidence | Basis for the estimate |
| --- | --- | --- | --- | --- |
| Data Migration | — | 15 – 20 | Low | Employee master, attendance history, leave balances, payroll history and documents. Scope unknown. A mid-year go-live also requires year-to-date import for TDS and PF. |

# 5. Development totals

| Group | Low | High | Share of effort |
| --- | --- | --- | --- |
| Foundation | 38 | 47 | 10 per cent |
| Employee lifecycle | 60 | 75 | 16 per cent |
| Time and attendance | 64 | 78 | 17 per cent |
| Compensation | 118 | 149 | 31 per cent |
| Supporting modules | 88 | 109 | 23 per cent |
| Data migration | 15 | 20 | 4 per cent |
| Development total | 383 | 478 | 100 per cent |

Four items account for roughly 30 per cent of the build: Payroll Processing, Reports, Attendance and Statutory. Three of those four carry Low confidence.

# 6. Effort beyond development

These are real costs and are not included in the figures above.

| Activity | Basis | Days |
| --- | --- | --- |
| Quality assurance and test cycles | 20 per cent of development | 77 – 96 |
| User acceptance testing and rework | 10 per cent of development | 38 – 48 |
| Project management and client meetings | 10 per cent of development | 38 – 48 |
| Deployment, environments, go-live | Fixed | 10 – 15 |
| Training and documentation | Fixed | 10 – 15 |
| Subtotal |  | 173 – 222 |

# 7. Total effort

| Component | Developer-days |
| --- | --- |
| Development | 383 – 478 |
| Beyond development | 173 – 222 |
| Total | 556 – 700 |

# 8. Calendar duration

Effort is not duration. Duration depends on team size and on how much work can genuinely run in parallel.

| Team size | Effective days per week | Working weeks | Calendar duration |
| --- | --- | --- | --- |
| 2 developers | 4 per developer | 70 – 88 | 16 – 20 months |
| 3 developers | 4 per developer | 46 – 58 | 11 – 13 months |
| 4 developers | 4 per developer | 35 – 44 | 8 – 10 months |
| 5 developers | 4 per developer | 28 – 35 | 7 – 8 months |

Four effective days per week, not five: meetings, code review, clarification and context switching consume the remainder. Estimating at five days is the most common cause of schedule overrun.

Adding developers beyond five produces waiting rather than throughput. The dependency chain is real: approvals block eight modules, attendance blocks leave, overtime and payroll, and payroll blocks statutory, outputs, compliance and half the reports.

Recommendation: four developers, delivering in eight to ten months.

# 9. Suggested phasing

Order is set by dependency, not preference.

| Phase | Contents | Days | Cumulative |
| --- | --- | --- | --- |
| 1 | Foundation — organization, access, approval engine, audit | 38 – 47 | 47 |
| 2 | Employee core — employee, lifecycle, letters, separation, onboarding | 42 – 53 | 100 |
| 3 | Time — shift and holiday, attendance, leave, overtime, comp-off | 64 – 78 | 178 |
| 4 | Pay — salary structure, payroll engine, statutory, deductions, loans, tax, outputs | 98 – 125 | 303 |
| 5 | Extended — recruitment, contract payroll, benefits, self service, documents | 58 – 71 | 374 |
| 6 | Output and compliance — reports, dashboards, statutory forms, L&D, visitor, notifications | 76 – 92 | 466 |
| 7 | Migration and go-live | 25 – 35 | 501 |

The first usable release arrives at the end of Phase 4 — an organization that can hire, manage employees, track attendance and run payroll. That is approximately 300 to 380 development days, or six to eight months with four developers.

# 10. Immediate opportunity: the Masters layer

Masters are the only major layer not blocked by the missing payroll formulas. They depend on knowing what fields and values exist, which complete master data and a complete requirements document would supply.

| Item | Count | Days |
| --- | --- | --- |
| Masters built and working today | 19 | — |
| Masters identified but not built | 28 | 30 |
| Prisma models and migration | about 20 models | 3 – 4 |
| Seeding real master data from the ERP export | — | 3 – 4 |
| Access control wiring | 28 nodes | 2 |
| Quality assurance | — | 8 |
| Total to complete the Masters layer | 47 masters | 46 – 48 |

With three developers this is four to five weeks. Masters parallelize almost linearly because the screens do not depend on one another.

One decision must be taken before building rather than after: whether rate and slab masters require effective dating. PF rates, ESI rates, professional tax, labour welfare fund and overtime slabs all change by notification, and payroll for a past month must use the rate then in force. Retrofitting version history onto a master after payroll consumes it is expensive.

# 11. Assumptions

1. The current technology stack continues: Next.js, Prisma, SQL Server and the existing component library.

2. Developers are familiar with the stack and require no ramp-up period.

3. The client answers open questions within days rather than weeks.

4. Requirements do not expand beyond the 203-screen sidebar plus the gaps already confirmed.

5. One production unit at go-live.

6. The eSSL biometric estate offers a usable integration path, whether by interface, database or file export.

# 12. Risks and opportunities

## 12.1 Risks that would increase the estimate

| Risk | Impact |
| --- | --- |
| Payroll formulas remain undocumented | Payroll engine could move from 30 to 60 days. Highest single risk in the project. |
| Multiple units go live together | Statutory registers, compliance forms and payroll all multiply. Add 15 to 25 per cent. |
| Full recruitment pipeline confirmed in scope | Add 10 to 12 days over the BRD-only reading. |
| Contract labour payroll requires separate statutory treatment | Could double the 10 to 12 days already allowed. |
| Double-machine incentive needs live production data | Cross-system integration. Add 8 to 15 days and a dependency on the ERP team. |
| Bank file format is non-standard | Two to three days for each additional format. |
| Mid-year go-live | Year-to-date import for TDS and PF. Add 10 to 15 days. |
| Attendance rules vary by department or category | Add 10 to 15 days to attendance alone. |

## 12.2 Opportunities that would reduce it

| Opportunity | Saving |
| --- | --- |
| Client supplies the payroll workbook with live formulas | Removes the largest uncertainty and may avoid 10 to 15 days of rework. |
| Client supplies a master-data export | Removes guesswork across three requirement topics. Saves 5 to 8 days. |
| Recruitment confirmed as offer-stage only | Saves 10 to 12 days. |
| Contract labour payroll deferred to a second phase | Saves 10 to 12 days. |
| Reports reduced from 36 to those actually used | Saves 15 to 18 days. |
| Eight simple lookups routed through the existing dropdown master | Saves 4 days in the Masters layer. |

# 13. Statement of confidence

Of the 32 management areas, eight are High confidence, fifteen are Medium and nine are Low.

The Low-confidence areas — attendance, leave, the payroll engine, statutory, recruitment, contract payroll, benefits and data migration — account for approximately 40 per cent of the total development estimate.

The range of 383 to 478 development days should therefore be read as indicative and not as a commitment.

A commitment-grade estimate becomes possible once three inputs are received:

1. The payroll formula sheet, or one completed payroll month with the matching payslips.

2. A data-only export of the master tables from the existing ERP.

3. Answers to the attendance and leave rule questions already recorded in the requirements decisions log.

With those three inputs the range should narrow to within approximately 15 per cent.

Prepared 25 August 2026. Supporting detail is held in the project documentation: requirements decisions log, legacy ERP schema analysis, build estimate and masters completion plan.